## Cronograma - Table 1
SCHEDULE | % | JANUARY |  |  |  | FEBRUARY | [7 empty] | MARCH | [9 empty] | April | [7 empty] | May
|  | W1 |  | W2 |  | W3 |  | W4 |  | W5 |  | W6 |  | W7 |  | W8 |  | W9 |  | W10 |  | W11 |  | W12 |  | W13 |  | W14 |  | W15 |  | W16 |  | W17
|  | 18 | 22 | 25 | 29 | 1 | 5 | 8 | 12 | 15 | 19 | 22 | 26 | 1 | 5 | 8 | 12 | 15 | 19 | 22 | 26 | 29 | 31 | 5 | 9 | 12 | 16 | 20 | 23 | 26 | 30 | 5 | 9 | 12 | 16
Analysis | 100
Initial Analysis | 100
Travel to Iquitos - Information Gathering | 100
Documented analysis | 100
Module/Reports UI design | 50
Conceptualization of screens | 100
Final design of screens | 0
Current system revision | 100
Functional Analysis | 100
Technical Analysis | 100
User administration | 45
Login Development | 100
Registration Development | 80
Dashboard Development | 0
Users Administration Development | 0
Business logic model | 50
Data Model | 80
Tables | 60
Managers | 30
Fixtures | 30
Screens | 0
Construction of HTML websites + CSS | 0
Searching of travels (type, date and transport filters) | 0
Log Update (Hours, dates, fuel) | 0
Visualization of Transport Log by type of trasnport and date (by air only) | 0
Scheduling and re/scheduling of passengers | 0
Data entry interfaces | 0
Register of travel schedules (by air/river, dates, stops) | 0
Manifest Registration (Company, cost and weight center for passengers and cargo) | 0
Presentations for the client | 0
Presentation 1 | 0
Presentation 2 | 0
Presentation 3 | 0
Aplication of changes | 0
Reports | 0.38462
Analysis of the Report | 5
Report 1 | 0
Report 2 | 0
Report 3 | 0
Report 4 | 0
Report 5 | 0
Report 6 | 0
Report 7 | 0
Report 8 | 0
Report 9 | 0
Report 10 | 0
Report 11 | 0
Report 12 | 0
User testing and adjustments | 0
Tests with user 1 | 0
Tests with user 2 | 0
Final tests with user | 0
Data migration | 0
Staging Install | 0
Production Install | 0
Documentation | 3.3333
Technical documentation | 10
User documentation | 0
Disaster Recovery Guide | 0

## Cronograma - Table 1_2
SCHEDULE | % | JANUARY |  |  |  | FEBRUARY | [7 empty] | MARCH | [9 empty] | April | [7 empty] | May
|  | W1 |  | W2 |  | W3 |  | W4 |  | W5 |  | W6 |  | W7 |  | W8 |  | W9 |  | W10 |  | W11 |  | W12 |  | W13 |  | W14 |  | W15 |  | W16 |  | W17
|  | 18 | 22 | 25 | 29 | 1 | 5 | 8 | 12 | 15 | 19 | 22 | 26 | 1 | 5 | 8 | 12 | 15 | 19 | 22 | 26 | 29 | 31 | 5 | 9 | 12 | 16 | 20 | 23 | 26 | 30 | 5 | 9 | 12 | 16
Analysis | 100
Initial Analysis | 100
Travel to Iquitos - Information Gathering | 100
Documented analysis | 100
Module/Reports UI design | 75
Conceptualization of screens | 100
Final design of screens | 50
Current system revision | 100
Functional Analysis | 100
Technical Analysis | 100
User administration | 92.5
Login Development | 100
Registration Development | 100
Dashboard Development | 90
Users Administration Development | 80
Business logic model | 100
Data Model | 100
Tables | 100
Managers | 100
Fixtures | 100
Applicacion development | 60
Dashboard | 95
Master objects | 95
Data entry interfaces | 50
Reports | 60
Adjustments | 0
Functional Analysis (New format) | 90
Mockups | 100
Design | 80
Presentations for the client | 40
Presentation 1 | 100
Presentation 2 | 100
Presentation 3 | 0
Presentation 4 | 0
Aplication of changes | 0
Reports | 52.5
Analysis of the Report | 90
Report 1part | 70
Report 2part | 50
Report 3part | 0
User testing and adjustments | 20
Tests with user 1 | 40
Final tests with user | 0
Data migration | 25
Staging Install | 0
Production Install | 0
Documentation | 25
Technical documentation | 40
User documentation | 35
Disaster Recovery Guide | 0
2450 | 30
3900 | 39
62.82% | 76.92%